## general_report
2014.3_Security_Priorities (jira.benefitfocus.com)
Displaying 8 issues at 05/22/2014 01:40 PM.
Key | Priority | Component Priority | Summary | Component/s | Fix Version/s | Status | Assignee | Requirements Lead | Est. Requirements Effort | Est. Design Effort | Est. Database Effort | Est. Application Effort | Est. Test Execution Effort
ERS-93424 | Major | 1 | Supplemental Market Segments to Restrict Carrier Representative Access | Engineer/PM | 2014.3-Request | Open | David Thorn | Susan Childress | 12 | 12 | 6 | 48 | 48
ERS-99604 | Critical | 1 | GLOBAL ¦ ‘Benefitfocus Associate’ Field Defaulted To “Yes” And Is Non-Editable -- New Carrier Representative User Account Creation | Carrier Ops - Focus | 2014.2-EE | Candidate | Joshua Stoltzfus | Susan Childress | 12 | 6 |  | 42 | 18
ERS-99777 | Major | 2 | Information Leakage In Password Reset Function | Engineer/PM | 2014.3-EE | Open | Wolfgang Sanyer | Susan Childress |  | 6 |  | 24 | 24
ERS-101681 | Major | 3 | Mask Sensitive Information Fields From Being Fully Shown In Web Pages | Engineer/PM | 2014.3-Request | Open | Wolfgang Sanyer | Susan Childress
ERS-101319 | Major | 4 | Enable CSRF Protection for Multiple URLs | Engineer/PM | Support | Open | Wolfgang Sanyer | Susan Childress |  | 3 |  | 25 | 20
ERS-86377 | Critical | 5 | Benefitfocus Associate User Accounts Creation/Editing Standardization | Engineer/PM | 2013.4-Request | Open | eEnrl Web PM - Prioritization | Susan Childress |  |  | 12 | 66 | 66
ERS-97003 | Major | 7 | Audit History Report Enhancement - Changes Made By Admin Users | Engineer/PM |  | Open | Stockton Robertson | Susan Childress | 12 | 6 | 30 | 42 | 30
ERS-80983 | Critical | 8 | Effective Dates for Temporary User Accounts | Engineer/PM | 2013.4-Request | Open | Justin Verona | Stockton Robertson |  |  | 6 | 72 | 42
Generated at Thu May 22 13:40:18 EDT 2014 by Wolfgang Sanyer using JIRA 5.0.1#721-sha1:838c4a0b95816e00f959efadbfe32a2139ca3829.